## general_report
JIRA
Displaying 24 issues at 07/Jul/15 4:19 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Epic Status | Epic Color | Rank | Iteration | Test Sessions | Raised During | Story Points | Business Value | Sprint | Epic Name | Epic Link | [CHART] Date of First Response | Testing Status | Account | Team | Flagged | Epic/Theme
FoodRecall | FOOD-1 | Create home page where users can search for food recalls | Story | Done | Medium | Done | Minks-Brown | Yana Beranek | Yana Beranek | 2015-06-29 16:23 | 2015-07-07 04:19 | 2015-07-02 16:15 | 2015-07-02 16:15 |  |  |  |  | 0 | 1 | [5 empty] | FOOD-8, FOOD-14 |  |  | Create home page where users can search for a food recall. User can search by state where product was distributed. User can search by food type or product name | [9 empty] | 0¦i000ac: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-2 | Create search results landing page | Story | Done | Medium | Done | Minks-Brown | Yana Beranek | Yana Beranek | 2015-06-29 16:26 |  | 2015-07-02 16:15 | 2015-07-02 16:15 |  |  |  |  | 0 | 2 | [5 empty] | FOOD-9, FOOD-13 |  |  | User can review search results which will include: Product name Product information Recalling firm name Reason for recall Date recall was initiated Severity of food recall health risk States where recalled food was distributed | [9 empty] | 0¦i000ac:r | None |  |  |  |  | Sprint 1 |  |  | 2015-06-30 11:06 | Not Started | None | None
FoodRecall | FOOD-3 | User can review details of food recall event | Story | Done | Medium | Done | Minks-Brown | Yana Beranek | Yana Beranek | 2015-06-29 16:30 |  | 2015-07-02 16:15 | 2015-07-02 16:15 |  |  |  |  | 0 | 2 | [5 empty] | FOOD-10 |  |  | User can review the following details of a food recall event: Recalling firm Recall initiation date Product description Where product was distributed Unique product IDs like lot number of sell-by dates Reason for recall Severity of health risk related to food recall Information about what they should do with the product Information about how to get a refund of their money for the product | [9 empty] | 0¦i000ac:i | None |  |  |  |  | Sprint 1 |  |  | 2015-06-30 11:09 | Not Started | None | None
FoodRecall | FOOD-4 | User can sign up for text alerts about food recalls | Story | Done | Medium | Done | Minks-Brown | Yana Beranek | Yana Beranek | 2015-06-29 16:32 |  | 2015-07-02 16:14 | 2015-07-02 16:14 |  |  |  |  | 0 | 2 | [5 empty] | FOOD-11, FOOD-15 |  |  | User can sign up for text alerts related to food recalls. User can choose to narrow their alert based on: Location Severity of health risk for food recall Type of food | [9 empty] | 0¦i000ac:v | None |  |  |  |  | Sprint 1 |  |  | 2015-06-30 11:09 | Not Started | None | None
FoodRecall | FOOD-5 | Conduct survey of consumers about food recall alerts | Story | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-29 16:35 |  | 2015-06-30 16:50 | 2015-06-30 16:50 |  |  |  |  | 0 | 1 | [5 empty] | FOOD-12, FOOD-20 | [12 empty] | 0¦i000ab: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-6 | Conduct UX Testing with users | Story | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-29 16:35 |  | 2015-07-02 08:47 | 2015-07-02 08:47 |  |  |  |  | 0 | 1 | [5 empty] | FOOD-16, FOOD-17, FOOD-18, FOOD-19 |  |  | Conduct testing with clickable prototype | [9 empty] | 0¦i000ad: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-7 | Create visual design style tile for FDA Alert: Food | Story | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-29 16:36 |  | 2015-07-01 15:51 | 2015-06-30 08:59 |  |  |  |  | 0 | 1 | _thumb_10121.png | [17 empty] | 0¦i000aj: | None | [8 empty] | Not Started | None | None
FoodRecall | FOOD-8 | FOOD-1 Create visual design | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-29 16:36 |  | 2015-07-01 15:43 | 2015-07-01 15:43 |  |  |  |  | 0 | 1 | _thumb_10115.png _thumb_10116.png _thumb_10117.png | [17 empty] | 0¦i000bb: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-9 | FOOD-2 Create visual design | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-29 16:37 |  | 2015-07-01 15:55 | 2015-07-01 15:55 |  |  |  |  | 0 | 1 | _thumb_10118.png _thumb_10119.png _thumb_10120.png | [17 empty] | 0¦i000bj: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-10 | FOOD-3 Create visual design | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-29 16:37 |  | 2015-07-02 11:38 | 2015-07-02 11:38 |  |  |  |  | 0 | 1 | _thumb_10123.png _thumb_10124.png _thumb_10125.png | [17 empty] | 0¦i000br: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-11 | FOOD-4 Create visual design | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-29 16:37 |  | 2015-07-02 11:41 | 2015-07-02 11:41 |  |  |  |  | 0 | 1 | _thumb_10126.png | [17 empty] | 0¦i000bz: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-12 | FOOD-5 Develop survey and launch | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-29 16:37 |  | 2015-06-30 16:37 | 2015-06-30 16:37 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000c7: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-13 | FOOD-2 Modify design based on user testing | Sub-task | Done | Medium | Done | Minks-Brown | Yana Beranek | Yana Beranek | 2015-06-30 16:23 |  | 2015-07-01 11:45 | 2015-07-01 11:45 |  |  |  |  | 0 | 1 | [8 empty] | Added a revised search functionality that allows user to search by product and location concurrently. | [9 empty] | 0¦i000cf: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-14 | FOOD-1 Modify design based on user testing | Sub-task | Done | Medium | Done | Minks-Brown | Yana Beranek | Yana Beranek | 2015-06-30 16:23 |  | 2015-07-02 16:13 | 2015-07-01 11:40 |  |  |  |  | 0 | 2 | [8 empty] | Added a revised search functionality that allows user to search by product and location concurrently. | [9 empty] | 0¦i000cn: | None |  |  |  |  | Sprint 1 |  |  | 2015-07-02 15:55 | Not Started | None | None
FoodRecall | FOOD-15 | FOOD-4 Modify design based on user testing | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-30 16:24 |  | 2015-07-02 11:46 | 2015-07-02 11:46 |  |  |  |  | 0 | 1 | [8 empty] | Created before testing. Was not needed. | [9 empty] | 0¦i000cv: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-16 | FOOD-6 Create user testing research guide | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-30 16:25 |  | 2015-06-30 16:27 | 2015-06-30 16:27 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000d3: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-17 | FOOD-6 Conduct ux testing | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-30 16:25 |  | 2015-07-01 09:08 | 2015-07-01 09:08 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000db: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-18 | FOOD-6 Compile findings and recommended design modifications | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-30 16:26 |  | 2015-07-02 08:47 | 2015-07-02 08:47 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000dj: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-19 | FOOD-6 Recruit test participants | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-30 16:26 |  | 2015-06-30 16:27 | 2015-06-30 16:27 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000dr: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-20 | FOOD-5 Summarize findings | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-30 16:37 | 2015-07-02 10:35 | 2015-06-30 16:49 | 2015-06-30 16:49 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000dz: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-21 | Develop front end code | Story | In Progress | Medium | Unresolved | Yana Beranek | Yana Beranek | Yana Beranek | 2015-07-06 10:46 |  | 2015-07-06 10:54 | [5 empty] | 0 | 1 | [5 empty] | FOOD-22, FOOD-23 |  |  | Develop front end code in HTML and hook up to api data | [9 empty] | 0¦i000ag: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-22 | FOOD-21 Develop front end code | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-07-06 10:48 |  | 2015-07-06 10:52 | 2015-07-06 10:50 |  |  |  |  | 0 | 1 | [8 empty] | Code attached for the homepage, search results page, recall details page and mobile sign-up for recall alerts page. | [9 empty] | 0¦i000en: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-23 | FOOD-21 Integrate front-end code with back-end dev | Sub-task | Done | Medium | Done | Scott Prenger | Yana Beranek | Yana Beranek | 2015-07-06 10:48 |  | 2015-07-06 19:52 | 2015-07-06 19:52 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i000ev: | None |  |  |  |  | Sprint 1 |  |  |  | Not Started | None | None
FoodRecall | FOOD-24 | Details page Product Identification | Task | To Do | Medium | Unresolved | Yana Beranek | Scott Prenger | Scott Prenger | 2015-07-06 16:02 | 2015-07-07 04:12 | 2015-07-06 16:06 | [5 empty] | 0 | 2 | [8 empty] | The Details page has a section entitled "Product Identification". Where does this information originate in the OpenFDA Food results? | [9 empty] | 0¦i000f3: | None | [7 empty] | 2015-07-06 16:06 | Not Started | None | None
Generated at Tue Jul 07 04:19:56 CDT 2015 by James Deel [Administrator] using JIRA 6.5-OD-08-001#65007-sha1:1fc98468dfd18a5f35861f5c2ab67219b6b6f2f6.